## Schemetic
Sl. No. | Scheme Name | Scheme Code | Sector | Start Date | Status | Administrative Sanctioned |  |  |  | Expenditure Done
[6 empty] | Unskilled Wages | Skilled Wages | Materials | Total | Wage Amount | SSK Amount | Material Amount | Total
1 | Nursery for creating forest sapling at the land of Priyalal Sarkar at Beraberia | 3201009009/DP/321002040959185 | DP | 2020-10-17 | On Going | 152031 | 0 | 13518 | 165549 | 10224 | 0 | 2678.57 | 12902.57
2 | Re-excavetion of canal from land of prem Chand sarkar to near house of Prafulla Roy at Beraberia und | 3201009009/FP/320201060561863 | FP | 2020-09-06 | physical complete | 158075 | 0 | 4000 | 162075 | 0 | 0 | 2678.57 | 2678.57
3 | Re-Excavation Jagar Khal at Bhutpara XIII | 3201009009/FP/PP/1022058 | FP | 2021-02-05 | On Going | 426839 | 0 | 5000 | 431839 | 150057 | 7186.5 | 4000 | 161243.5
4 | EW for Jhupjhupi Khal at Bhutpara XIII | 3201009009/FP/PP/1022060 | FP | 2021-02-20 | On Going | 441600 | 0 | 5000 | 446600 | 257683 | 10075.5 | 4000 | 271758.5
5 | Excavation of fram pond II at the land of Priyolal Sarkar at Beraberia under Dogachhi GP | 3201009009/IF/321002041153118 | IF | 2020-07-28 | physical complete | 241827 | 0 | 3000 | 244827 | 0 | 0 | 2678.57 | 2678.57
6 | EW for Farm pod of Arabindu Sarkar at Mahishnangra | 3201009009/IF/321002041159278 | IF | 2020-07-28 | physical complete | 241827 | 0 | 3000 | 244827 | 0 | 4896 | 2678.57 | 7574.57
7 | Excavation of fram pond at the land of Nikhil Sarkar at Beraberia under Dogachhi GP | 3201009009/IF/321002041208807 | IF | 2020-11-11 | physical complete | 332959 | 0 | 3000 | 335959 | 0 | 7956 | 3000 | 10956
8 | Excavation of fram pond at the land of Anna Rani Sarkar at Mahishnangra under Dogachhi GP | 3201009009/IF/321002041208809 | IF | 2020-11-11 | physical complete | 272842 | 0 | 3000 | 275842 | 684 | 612 | 3000 | 4296
9 | Plantation of Lichi plant at the land of Subhash Chakrabarty at Goaldaha | 3201009009/IF/321002041279450 | IF | 2021-07-15 | On Going | 19016 | 0 | 3119 | 22135 | 18957 | 0 | 0 | 18957
10 | Plantation of Mango plant at the land of Soumick Chakrabarty at Goaldaha | 3201009009/IF/321002041279452 | IF | 2021-07-15 | On Going | 9508 | 0 | 3059 | 12567 | 9372 | 0 | 0 | 9372
11 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1904865 | 3201009009/IF/IAY/2121686 | IF | 2021-07-15 | Completed | 17190 | 0 | 0 | 17190 | 18360 | 0 | 0 | 18360
12 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2556926 | 3201009009/IF/IAY/3242683 | IF | 2021-06-17 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
13 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4513971 | 3201009009/IF/IAY/3242727 | IF | 2019-11-26 | Completed | 18360 | 0 | 0 | 18360 | 6120 | 0 | 0 | 6120
14 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2149209 | 3201009009/IF/IAY/3243335 | IF | 2020-01-14 | Completed | 18360 | 0 | 0 | 18360 | 2865 | 0 | 0 | 2865
15 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3394210 | 3201009009/IF/IAY/3300704 | IF | 2020-07-15 | Completed | 18360 | 0 | 0 | 18360 | 6120 | 0 | 0 | 6120
16 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3807111 | 3201009009/IF/IAY/3300923 | IF | 2019-12-17 | Completed | 18360 | 0 | 0 | 18360 | 17580 | 0 | 0 | 17580
17 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4039846 | 3201009009/IF/IAY/3301141 | IF | 2019-01-04 | Completed | 18360 | 0 | 0 | 18360 | 2865 | 0 | 0 | 2865
18 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5599956 | 3201009009/IF/IAY/3376057 | IF | 2020-04-15 | Completed | 18360 | 0 | 0 | 18360 | 3060 | 0 | 0 | 3060
19 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2143294 | 3201009009/IF/IAY/3405163 | IF | 2020-04-15 | Completed | 18360 | 0 | 0 | 18360 | 14715 | 0 | 0 | 14715
20 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5590662 | 3201009009/IF/IAY/3405253 | IF | 2020-04-15 | Completed | 18360 | 0 | 0 | 18360 | 3060 | 0 | 0 | 3060
21 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5041830 | 3201009009/IF/IAY/3704829 | IF | 2020-04-15 | Completed | 19170 | 0 | 0 | 19170 | 3060 | 0 | 0 | 3060
22 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3492068 | 3201009009/IF/IAY/3704837 | IF | 2020-04-01 | Completed | 19170 | 0 | 0 | 19170 | 3060 | 0 | 0 | 3060
23 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2198753 | 3201009009/IF/IAY/3704841 | IF | 2020-03-20 | Completed | 19170 | 0 | 0 | 19170 | 17580 | 0 | 0 | 17580
24 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3309112 | 3201009009/IF/IAY/4104980 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
25 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4048796 | 3201009009/IF/IAY/4104988 | IF | 2021-07-15 | Completed | 18360 | 0 | 0 | 18360 | 18360 | 0 | 0 | 18360
26 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3251171 | 3201009009/IF/IAY/4104989 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
27 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4523839 | 3201009009/IF/IAY/4104991 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
28 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3011001 | 3201009009/IF/IAY/4104992 | IF | 2021-06-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
29 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5752761 | 3201009009/IF/IAY/4116846 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
30 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3124123 | 3201009009/IF/IAY/4116848 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
31 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5676324 | 3201009009/IF/IAY/4116850 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
32 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5214072 | 3201009009/IF/IAY/4116856 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
33 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4955825 | 3201009009/IF/IAY/4116858 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
34 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5426001 | 3201009009/IF/IAY/4116861 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
35 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1481036 | 3201009009/IF/IAY/4116862 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
36 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5425118 | 3201009009/IF/IAY/4116866 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
37 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4628887 | 3201009009/IF/IAY/4116868 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
38 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5173531 | 3201009009/IF/IAY/4116872 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
39 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2299945 | 3201009009/IF/IAY/4116875 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
40 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3040400 | 3201009009/IF/IAY/4116876 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
41 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3061234 | 3201009009/IF/IAY/4116877 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
42 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4903554 | 3201009009/IF/IAY/4116880 | IF | 2020-06-29 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
43 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4131534 | 3201009009/IF/IAY/4116881 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
44 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1943005 | 3201009009/IF/IAY/4116882 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
45 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4816534 | 3201009009/IF/IAY/4116883 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
46 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5147923 | 3201009009/IF/IAY/4116884 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
47 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5758057 | 3201009009/IF/IAY/4116886 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
48 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4229647 | 3201009009/IF/IAY/4116887 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
49 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4969092 | 3201009009/IF/IAY/4116895 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
50 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4758161 | 3201009009/IF/IAY/4116898 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
51 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5629539 | 3201009009/IF/IAY/4116901 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
52 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2741051 | 3201009009/IF/IAY/4116902 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
53 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5343787 | 3201009009/IF/IAY/4116906 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
54 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2900377 | 3201009009/IF/IAY/4116910 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
55 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5309685 | 3201009009/IF/IAY/4116913 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
56 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4702880 | 3201009009/IF/IAY/4116914 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
57 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4077025 | 3201009009/IF/IAY/4116915 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
58 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5357883 | 3201009009/IF/IAY/4116920 | IF | 2021-04-10 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
59 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4891339 | 3201009009/IF/IAY/4116922 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 5916 | 0 | 0 | 5916
60 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5019051 | 3201009009/IF/IAY/4116923 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
61 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4510166 | 3201009009/IF/IAY/4116925 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
62 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5252833 | 3201009009/IF/IAY/4116930 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
63 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5728347 | 3201009009/IF/IAY/4116931 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
64 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5348673 | 3201009009/IF/IAY/4116933 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
65 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5724142 | 3201009009/IF/IAY/4116934 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
66 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5380807 | 3201009009/IF/IAY/4116935 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
67 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1259045 | 3201009009/IF/IAY/4116936 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
68 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5417457 | 3201009009/IF/IAY/4116939 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
69 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5629545 | 3201009009/IF/IAY/4116940 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
70 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5616123 | 3201009009/IF/IAY/4116942 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
71 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4948829 | 3201009009/IF/IAY/4116944 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
72 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5614372 | 3201009009/IF/IAY/4116945 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
73 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4646659 | 3201009009/IF/IAY/4116951 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18156 | 0 | 0 | 18156
74 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5310387 | 3201009009/IF/IAY/4117182 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
75 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5411056 | 3201009009/IF/IAY/4117184 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
76 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4853034 | 3201009009/IF/IAY/4117186 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
77 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4801093 | 3201009009/IF/IAY/4117191 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
78 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4132070 | 3201009009/IF/IAY/4117192 | IF | 2021-07-12 | Completed | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
79 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4850611 | 3201009009/IF/IAY/4117193 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
80 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4555753 | 3201009009/IF/IAY/4117195 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
81 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4023861 | 3201009009/IF/IAY/4117200 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
82 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2346997 | 3201009009/IF/IAY/4117201 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
83 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3267338 | 3201009009/IF/IAY/4117202 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
84 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2365299 | 3201009009/IF/IAY/4117207 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
85 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1480202 | 3201009009/IF/IAY/4117208 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
86 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1129579 | 3201009009/IF/IAY/4117210 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
87 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4592711 | 3201009009/IF/IAY/4117212 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
88 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4994020 | 3201009009/IF/IAY/4117213 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
89 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4452020 | 3201009009/IF/IAY/4117216 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
90 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4617442 | 3201009009/IF/IAY/4117220 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
91 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5617961 | 3201009009/IF/IAY/4117223 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
92 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4049560 | 3201009009/IF/IAY/4117231 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
93 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5035313 | 3201009009/IF/IAY/4117261 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
94 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5728677 | 3201009009/IF/IAY/4117263 | IF | 2021-10-01 | Completed | 19170 | 0 | 0 | 19170 | 12096 | 0 | 0 | 12096
95 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5641399 | 3201009009/IF/IAY/4117270 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
96 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2248108 | 3201009009/IF/IAY/4117273 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
97 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2592355 | 3201009009/IF/IAY/4117278 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
98 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2294933 | 3201009009/IF/IAY/4117283 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
99 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5387376 | 3201009009/IF/IAY/4117293 | IF | 2021-05-28 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
100 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3052250 | 3201009009/IF/IAY/4117295 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
101 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5704285 | 3201009009/IF/IAY/4117299 | IF | 2021-04-01 | Completed | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
102 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4646633 | 3201009009/IF/IAY/4117300 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
103 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5230768 | 3201009009/IF/IAY/4117303 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
104 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5704299 | 3201009009/IF/IAY/4117305 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
105 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5715303 | 3201009009/IF/IAY/4117319 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
106 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5445533 | 3201009009/IF/IAY/4117329 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
107 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4604571 | 3201009009/IF/IAY/4117330 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
108 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4903764 | 3201009009/IF/IAY/4117334 | IF | 2020-06-29 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
109 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4588355 | 3201009009/IF/IAY/4117341 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
110 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4851829 | 3201009009/IF/IAY/4117348 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
111 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5003143 | 3201009009/IF/IAY/4117355 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
112 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5737080 | 3201009009/IF/IAY/4117362 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
113 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2360065 | 3201009009/IF/IAY/4117365 | IF | 2021-07-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
114 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5147467 | 3201009009/IF/IAY/4117375 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
115 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5359904 | 3201009009/IF/IAY/4117382 | IF | 2020-12-17 | Completed | 18360 | 0 | 0 | 18360 | 12240 | 0 | 0 | 12240
116 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2556979 | 3201009009/IF/IAY/4117388 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
117 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5320118 | 3201009009/IF/IAY/4117390 | IF | 2020-12-17 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
118 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3097073 | 3201009009/IF/IAY/4117392 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
119 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4754641 | 3201009009/IF/IAY/4117393 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
120 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4266126 | 3201009009/IF/IAY/4117397 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
121 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2366011 | 3201009009/IF/IAY/4117399 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
122 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2110269 | 3201009009/IF/IAY/4117400 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
123 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5530532 | 3201009009/IF/IAY/4117402 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
124 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2504198 | 3201009009/IF/IAY/4117411 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
125 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5583387 | 3201009009/IF/IAY/4117414 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
126 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3846119 | 3201009009/IF/IAY/4117416 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
127 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5614357 | 3201009009/IF/IAY/4117419 | IF | 2020-11-26 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
128 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4245385 | 3201009009/IF/IAY/4117433 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
129 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5350553 | 3201009009/IF/IAY/4117436 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
130 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5372769 | 3201009009/IF/IAY/4117439 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
131 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5328325 | 3201009009/IF/IAY/4117455 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
132 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5621233 | 3201009009/IF/IAY/4117457 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
133 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5417511 | 3201009009/IF/IAY/4117458 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
134 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4268053 | 3201009009/IF/IAY/4117462 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
135 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2286514 | 3201009009/IF/IAY/4117465 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
136 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3045329 | 3201009009/IF/IAY/4117469 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
137 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5721397 | 3201009009/IF/IAY/4117478 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
138 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4099706 | 3201009009/IF/IAY/4117494 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
139 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5580546 | 3201009009/IF/IAY/4117498 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
140 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5551282 | 3201009009/IF/IAY/4117501 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
141 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4916821 | 3201009009/IF/IAY/4117502 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
142 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5692151 | 3201009009/IF/IAY/4117506 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
143 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5650622 | 3201009009/IF/IAY/4117509 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
144 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4802418 | 3201009009/IF/IAY/4117513 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
145 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5240733 | 3201009009/IF/IAY/4117515 | IF | 2020-07-06 | Completed | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
146 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2418077 | 3201009009/IF/IAY/4117541 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
147 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4345726 | 3201009009/IF/IAY/4117542 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
148 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5182350 | 3201009009/IF/IAY/4117556 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
149 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3328926 | 3201009009/IF/IAY/4117559 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
150 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2630805 | 3201009009/IF/IAY/4117561 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
151 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5315913 | 3201009009/IF/IAY/4117562 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
152 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3307389 | 3201009009/IF/IAY/4117603 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
153 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3151618 | 3201009009/IF/IAY/4117622 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
154 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3071475 | 3201009009/IF/IAY/4117646 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
155 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5147956 | 3201009009/IF/IAY/4117648 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
156 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5147577 | 3201009009/IF/IAY/4117671 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
157 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5366511 | 3201009009/IF/IAY/4117672 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
158 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5671560 | 3201009009/IF/IAY/4117673 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
159 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5158707 | 3201009009/IF/IAY/4117680 | IF | 2021-04-10 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
160 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4358044 | 3201009009/IF/IAY/4117702 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
161 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2418994 | 3201009009/IF/IAY/4117703 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
162 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5593386 | 3201009009/IF/IAY/4117707 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
163 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4563324 | 3201009009/IF/IAY/4117727 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
164 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1509353 | 3201009009/IF/IAY/4117729 | IF | 2020-07-28 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
165 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3290656 | 3201009009/IF/IAY/4117738 | IF | 2021-04-01 | Completed | 20070 | 0 | 0 | 20070 | 12036 | 0 | 0 | 12036
166 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5708783 | 3201009009/IF/IAY/4117742 | IF | 2020-12-17 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
167 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5676894 | 3201009009/IF/IAY/4117752 | IF | 2021-05-13 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
168 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2228137 | 3201009009/IF/IAY/4117759 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
169 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2898578 | 3201009009/IF/IAY/4379039 | IF | 2021-01-01 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
170 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2870166 | 3201009009/IF/IAY/4383904 | IF | 2020-12-17 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
171 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1420152 | 3201009009/IF/IAY/4384908 | IF | 2021-01-01 | Completed | 19170 | 0 | 0 | 19170 | 12240 | 0 | 0 | 12240
172 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2995581 | 3201009009/IF/IAY/4387601 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
173 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3151541 | 3201009009/IF/IAY/4388283 | IF | 2021-07-10 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
174 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4496395 | 3201009009/IF/IAY/4420490 | IF | 2020-12-17 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
175 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4395941 | 3201009009/IF/IAY/4421391 | IF | 2020-12-17 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
176 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4619661 | 3201009009/IF/IAY/4429003 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
177 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1963934 | 3201009009/IF/IAY/4583044 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
178 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4905999 | 3201009009/IF/IAY/4583045 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
179 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5302358 | 3201009009/IF/IAY/4583046 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
180 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5566589 | 3201009009/IF/IAY/4583058 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
181 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1230156 | 3201009009/IF/IAY/4583059 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
182 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2090035 | 3201009009/IF/IAY/4583064 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
183 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4757242 | 3201009009/IF/IAY/4583076 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
184 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5308022 | 3201009009/IF/IAY/4583077 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
185 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5244390 | 3201009009/IF/IAY/4583079 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
186 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5473089 | 3201009009/IF/IAY/4583261 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
187 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5641416 | 3201009009/IF/IAY/4583262 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 8976 | 0 | 0 | 8976
188 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4497134 | 3201009009/IF/IAY/4583270 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
189 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4954151 | 3201009009/IF/IAY/4583271 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
190 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5046781 | 3201009009/IF/IAY/4583279 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
191 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4604343 | 3201009009/IF/IAY/4583280 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
192 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4058047 | 3201009009/IF/IAY/4646299 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
193 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4699581 | 3201009009/IF/IAY/4659153 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
194 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5766413 | 3201009009/IF/IAY/4659343 | IF | 2021-07-10 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
195 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4496414 | 3201009009/IF/IAY/4659344 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
196 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4370851 | 3201009009/IF/IAY/4659345 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
197 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1542102 | 3201009009/IF/IAY/4659347 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
198 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1674804 | 3201009009/IF/IAY/4659349 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
199 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4105482 | 3201009009/IF/IAY/4659394 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
200 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2227658 | 3201009009/IF/IAY/4659395 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
201 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3124107 | 3201009009/IF/IAY/4659400 | IF | 2021-04-04 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
202 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3043818 | 3201009009/IF/IAY/4659401 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
203 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1418011 | 3201009009/IF/IAY/4659523 | IF | 2022-02-17 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
204 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4492746 | 3201009009/IF/IAY/4659525 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
205 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3426004 | 3201009009/IF/IAY/4659534 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
206 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1346784 | 3201009009/IF/IAY/4659556 | IF | 2022-02-17 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
207 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3329568 | 3201009009/IF/IAY/4659996 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
208 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1662393 | 3201009009/IF/IAY/4659997 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
209 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3178264 | 3201009009/IF/IAY/4660000 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
210 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3448042 | 3201009009/IF/IAY/4660042 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
211 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5429643 | 3201009009/IF/IAY/4660061 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
212 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2566726 | 3201009009/IF/IAY/4660062 | IF | 2021-07-10 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
213 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5642162 | 3201009009/IF/IAY/4710591 | IF | 2021-07-10 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
214 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3872154 | 3201009009/IF/IAY/4710592 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
215 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3971213 | 3201009009/IF/IAY/4710594 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
216 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3058490 | 3201009009/IF/IAY/4710595 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
217 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2281384 | 3201009009/IF/IAY/4710596 | IF | 2021-07-15 | On Going | 19170 | 0 | 0 | 19170 | 9180 | 0 | 0 | 9180
218 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5197375 | 3201009009/IF/IAY/4710597 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
219 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4113708 | 3201009009/IF/IAY/4710602 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
220 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4131525 | 3201009009/IF/IAY/4710603 | IF | 2021-05-28 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
221 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3951703 | 3201009009/IF/IAY/4710604 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
222 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4125679 | 3201009009/IF/IAY/4710605 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
223 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3630026 | 3201009009/IF/IAY/4743713 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
224 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5648285 | 3201009009/IF/IAY/4744215 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
225 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5660205 | 3201009009/IF/IAY/4744216 | IF | 2021-05-13 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
226 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5096930 | 3201009009/IF/IAY/4794723 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
227 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5439848 | 3201009009/IF/IAY/4794724 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
228 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4782844 | 3201009009/IF/IAY/4794853 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
229 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3257111 | 3201009009/IF/IAY/4794854 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
230 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2179570 | 3201009009/IF/IAY/4794855 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
231 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3260545 | 3201009009/IF/IAY/4794856 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
232 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4779540 | 3201009009/IF/IAY/4794962 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
233 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5410562 | 3201009009/IF/IAY/4795016 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
234 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3822226 | 3201009009/IF/IAY/4795017 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
235 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4523857 | 3201009009/IF/IAY/4795073 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
236 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1665342 | 3201009009/IF/IAY/4795074 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
237 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3771889 | 3201009009/IF/IAY/4795075 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
238 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1272330 | 3201009009/IF/IAY/4795076 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
239 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3124896 | 3201009009/IF/IAY/4795077 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
240 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3283413 | 3201009009/IF/IAY/4795140 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
241 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4871966 | 3201009009/IF/IAY/4795141 | IF | 2021-10-27 | On Going | 20070 | 0 | 0 | 20070 | 15705 | 0 | 0 | 15705
242 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3251834 | 3201009009/IF/IAY/4795252 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
243 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4891191 | 3201009009/IF/IAY/4795253 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
244 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2591558 | 3201009009/IF/IAY/4795254 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
245 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4782113 | 3201009009/IF/IAY/4795305 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
246 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4566975 | 3201009009/IF/IAY/4795306 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
247 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5425126 | 3201009009/IF/IAY/4795364 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
248 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2591711 | 3201009009/IF/IAY/4795365 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
249 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2292121 | 3201009009/IF/IAY/4795366 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
250 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4862459 | 3201009009/IF/IAY/4795417 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
251 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4993107 | 3201009009/IF/IAY/4795418 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
252 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3293942 | 3201009009/IF/IAY/4795514 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
253 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4796659 | 3201009009/IF/IAY/4795515 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
254 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3313492 | 3201009009/IF/IAY/4795568 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18495 | 0 | 0 | 18495
255 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4395480 | 3201009009/IF/IAY/4795634 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
256 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4245208 | 3201009009/IF/IAY/4795635 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
257 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5673292 | 3201009009/IF/IAY/4795700 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
258 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1633556 | 3201009009/IF/IAY/4795759 | IF | 2021-07-15 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
259 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5019188 | 3201009009/IF/IAY/4795760 | IF | 2021-07-15 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
260 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2258065 | 3201009009/IF/IAY/4798831 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
261 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2451181 | 3201009009/IF/IAY/4804233 | IF | 2021-06-01 | Completed | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
262 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4846261 | 3201009009/IF/IAY/4804234 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
263 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5046608 | 3201009009/IF/IAY/4804235 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
264 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5404457 | 3201009009/IF/IAY/4804236 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
265 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5034942 | 3201009009/IF/IAY/4804237 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
266 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3071297 | 3201009009/IF/IAY/4804238 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
267 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4674623 | 3201009009/IF/IAY/4804239 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
268 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4801392 | 3201009009/IF/IAY/4804240 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
269 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5343820 | 3201009009/IF/IAY/4804241 | IF | 2021-06-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
270 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5424556 | 3201009009/IF/IAY/4804242 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
271 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5347184 | 3201009009/IF/IAY/4804243 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
272 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2587250 | 3201009009/IF/IAY/4804244 | IF | 2021-06-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
273 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5667119 | 3201009009/IF/IAY/4804245 | IF | 2021-06-01 | On Going | 19170 | 0 | 0 | 19170 | 15300 | 0 | 0 | 15300
274 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5220715 | 3201009009/IF/IAY/4804246 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
275 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5642767 | 3201009009/IF/IAY/4804247 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 6120 | 0 | 0 | 6120
276 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4026437 | 3201009009/IF/IAY/4804248 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
277 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3058867 | 3201009009/IF/IAY/4804249 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
278 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3309416 | 3201009009/IF/IAY/4804250 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
279 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5608410 | 3201009009/IF/IAY/4804251 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
280 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5695083 | 3201009009/IF/IAY/4804252 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
281 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3871095 | 3201009009/IF/IAY/4804253 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
282 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5223876 | 3201009009/IF/IAY/4804254 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
283 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4571759 | 3201009009/IF/IAY/4804255 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
284 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3348680 | 3201009009/IF/IAY/4804256 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
285 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4099742 | 3201009009/IF/IAY/4804259 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 12240 | 0 | 0 | 12240
286 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4632179 | 3201009009/IF/IAY/4804260 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
287 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4902253 | 3201009009/IF/IAY/4804261 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
288 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4827698 | 3201009009/IF/IAY/4804262 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
289 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2349967 | 3201009009/IF/IAY/4804263 | IF | 2021-04-01 | Completed | 19170 | 0 | 0 | 19170 | 18360 | 0 | 0 | 18360
290 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5593382 | 3201009009/IF/IAY/4804264 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
291 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5723131 | 3201009009/IF/IAY/4804265 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 9180 | 0 | 0 | 9180
292 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5385317 | 3201009009/IF/IAY/4804266 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
293 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4004125 | 3201009009/IF/IAY/4804267 | IF | 2021-04-01 | On Going | 20070 | 0 | 0 | 20070 | 15300 | 0 | 0 | 15300
294 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3249413 | 3201009009/IF/IAY/4851430 | IF | 2021-10-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
295 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2631820 | 3201009009/IF/IAY/4853032 | IF | 2021-10-27 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
296 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5582192 | 3201009009/IF/IAY/4853033 | IF | 2021-10-27 | On Going | 20070 | 0 | 0 | 20070 | 9585 | 0 | 0 | 9585
297 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3106367 | 3201009009/IF/IAY/4853034 | IF | 2021-10-27 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
298 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3496002 | 3201009009/IF/IAY/4853035 | IF | 2021-10-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
299 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2702707 | 3201009009/IF/IAY/4859527 | IF | 2021-09-27 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
300 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2729577 | 3201009009/IF/IAY/4859566 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
301 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3412371 | 3201009009/IF/IAY/4860655 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
302 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3427789 | 3201009009/IF/IAY/4860683 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
303 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4845625 | 3201009009/IF/IAY/4864724 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
304 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4893958 | 3201009009/IF/IAY/4864917 | IF | 2021-09-27 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
305 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5186776 | 3201009009/IF/IAY/4866102 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
306 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5410705 | 3201009009/IF/IAY/4866976 | IF | 2021-09-27 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
307 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2692272 | 3201009009/IF/IAY/4872314 | IF | 2021-10-11 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
308 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2817851 | 3201009009/IF/IAY/4872364 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
309 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3295445 | 3201009009/IF/IAY/4872558 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
310 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3670836 | 3201009009/IF/IAY/4872734 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
311 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4617507 | 3201009009/IF/IAY/4873901 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
312 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4716969 | 3201009009/IF/IAY/4873977 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
313 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4801437 | 3201009009/IF/IAY/4874041 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
314 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4812448 | 3201009009/IF/IAY/4874053 | IF | 2021-10-11 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
315 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4895195 | 3201009009/IF/IAY/4874136 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 9585 | 0 | 0 | 9585
316 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5208377 | 3201009009/IF/IAY/4874427 | IF | 2021-10-11 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
317 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5210624 | 3201009009/IF/IAY/4874432 | IF | 2021-10-11 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
318 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5429372 | 3201009009/IF/IAY/4874678 | IF | 2021-10-01 | On Going | 19170 | 0 | 0 | 19170 | 12780 | 0 | 0 | 12780
319 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5487155 | 3201009009/IF/IAY/4874786 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
320 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5513065 | 3201009009/IF/IAY/4874867 | IF | 2021-10-11 | On Going | 20070 | 0 | 0 | 20070 | 9585 | 0 | 0 | 9585
321 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2561687 | 3201009009/IF/IAY/4921831 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
322 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB2908446 | 3201009009/IF/IAY/4922261 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
323 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3125123 | 3201009009/IF/IAY/4922602 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
324 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3630155 | 3201009009/IF/IAY/4923334 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 9585 | 0 | 0 | 9585
325 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB3805390 | 3201009009/IF/IAY/4923555 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
326 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4430699 | 3201009009/IF/IAY/4924301 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
327 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5225408 | 3201009009/IF/IAY/4928043 | IF | 2021-10-01 | Completed | 20070 | 0 | 0 | 20070 | 12780 | 0 | 0 | 12780
328 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB1956557 | 3201009009/IF/IAY/4953157 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
329 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4045640 | 3201009009/IF/IAY/4968268 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
330 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB4513850 | 3201009009/IF/IAY/4972318 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
331 | Construction of PMAY-G House for Individuals -PMAY-G REG. NO. WB5316133 | 3201009009/IF/IAY/4984907 | IF | 2021-10-01 | On Going | 20070 | 0 | 0 | 20070 | 6390 | 0 | 0 | 6390
332 | Const. of J.B road with E/W from shop of Subol Sarkar to Idgartala at Goaldaha under Dogachhi GP | 3201009009/RC/320201060595827 | RC | 2021-01-23 | Completed | 43585 | 4241 | 295606 | 343432 | 582 | 8364 | 257250 | 266196
333 | Const. of J.B road with E/W from land of Kalicharan Halder to land of Siraj Sk at Goaldaha under DG | 3201009009/RC/320201060595828 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 591 | 8364 | 219111.25 | 228066.25
334 | Const. of J.B road with E/W and hume pipe from P.M.G.S.Y. road to pond of Bhim Sarkar at Mahishnan | 3201009009/RC/320201060595829 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 585 | 8364 | 256296.25 | 265245.25
335 | Const. of J.B road with E/W and hume pipe from pond of Bhim Sarkar to H/O Rasomoy Sarkar at Berabe | 3201009009/RC/320201060595830 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 588 | 8364 | 256497.5 | 265449.5
336 | Const. of J.B road with E/W and hume pipe from H/O Rosomoy Sarkar to land of Bhim Sarkar at breaber | 3201009009/RC/320201060595831 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 612 | 8364 | 248185 | 257161
337 | Const. of J.B road with E/W and hume pipe from land of Bhim Sarkar to H/O Mahadeb Baidya at Berabe | 3201009009/RC/320201060595832 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 1194 | 8364 | 231580 | 241138
338 | Const. of J.B road with E/W and hume pipe from Mahadeb Baidya to H/O Gopal Biswas at Beraberia | 3201009009/RC/320201060595833 | RC | 2021-01-23 | Completed | 46620 | 4208 | 292974 | 343802 | 364 | 6732 | 236310 | 243406
339 | Const. of J.B road with E/W from Islam sk to land of Ahamed sk at Natungram under Dogachhi GP | 3201009009/RC/320201060595835 | RC | 2021-02-08 | Completed | 45913 | 4219 | 293683 | 343815 | 612 | 8364 | 257600 | 266576
340 | Const. of J.B road with E/W from Land of Ahamed sk to land of Alim Sk at Natungram under Dogachhi | 3201009009/RC/320201060595836 | RC | 2021-02-11 | Completed | 46175 | 4219 | 293683 | 344077 | 0 | 8364 | 257241.25 | 265605.25
341 | Const. of J.B road with E/W from Land of Alim Sk to land of Gopal Sarkar at Natungram under Dogach | 3201009009/RC/320201060595837 | RC | 2021-02-11 | Completed | 47564 | 4197 | 292266 | 344027 | 580 | 8364 | 240817.5 | 249761.5
342 | Const. of J.B road with E/W fromLand of Gopal Sarkar to Land of Surat Ali Sk at Natungram under Do | 3201009009/RC/320201060595838 | RC | 2021-02-08 | Completed | 48002 | 4186 | 291557 | 343745 | 0 | 6324 | 243346.25 | 249670.25
343 | Const. of J.B road with E/W from Curlvert to Bimal Sardar under Dogachhi GP | 3201009009/RC/320201060595840 | RC | 2021-02-17 | Completed | 44874 | 4164 | 290140 | 339178 | 1128 | 6936 | 250188.75 | 258252.75
344 | Const. of J.B road with E/W from H/O Prasanta Bhakta to land of Monoranjan Barui at Beraberia un | 3201009009/RC/320201060595841 | RC | 2021-02-02 | Completed | 43306 | 4252 | 295808 | 343366 | 612 | 8364 | 253050 | 262026
345 | Const. of J.B road with E/W from Land of Monoranjan Barui to land of Bhulu Mondal at Beraberia und | 3201009009/RC/320201060595842 | RC | 2021-02-05 | Completed | 43486 | 4241 | 295100 | 342827 | 612 | 8364 | 253128.75 | 262104.75
346 | Const. of J.B road with E/W from Bablu Sardar to Gobinda Sardar under Dogachhi GP | 3201009009/RC/320201060595845 | RC | 2021-01-23 | Completed | 48898 | 4131 | 288015 | 341044 | 585 | 6936 | 252157.5 | 259678.5
347 | Earth work for road with Jhama Bats from the kall ghar of Bhim Sarkar to the Pond of Priyolal Sarkar | 3201009009/RC/320201060618251 | RC | 2021-07-07 | On Going | 159471 | 2262 | 179771 | 341504 | 153584 | 0 | 0 | 153584
348 | Earthwork for road with Jhama Bats from the HO Rabi Sardar to the HO Samar Sardar at Butpara | 3201009009/RC/GIS/1386291 | RC | 2021-08-18 | On Going | 158571 | 2249 | 175084 | 335904 | 137393 | 0 | 0 | 137393
349 | Earthwork for road with Jhama Bats from the HO Suroj Sardar to the HO Bhola Sardar at Butpara | 3201009009/RC/GIS/1386321 | RC | 2021-08-18 | On Going | 157670 | 2236 | 174168 | 334074 | 132665 | 639 | 0 | 133304
350 | Earthwork for road with Jhama Bats from the HO Aswin Sardar to the HO Dilip Sardar at Butpara | 3201009009/RC/GIS/1386337 | RC | 2021-10-02 | On Going | 160373 | 2275 | 176914 | 339562 | 136143 | 0 | 0 | 136143
351 | Earthwork for road with Jhama Bats from the HO Prafulla Barui to the HO Prem Chand Sarkar at Berab | 3201009009/RC/GIS/1388721 | RC | 2021-08-23 | On Going | 161273 | 2288 | 177829 | 341390 | 147403 | 0 | 0 | 147403
352 | Earthwork for road with Jhama Bats from the LO Kartick Mondal to the HO Prafulla Barui at Beraberi | 3201009009/RC/GIS/1388738 | RC | 2021-07-15 | On Going | 161273 | 2288 | 177829 | 341390 | 151828 | 0 | 0 | 151828
353 | Earthwork for road with Jhama Bats from the HO Narugopal Ray to the HO Subhash Ray at Mahishnangra | 3201009009/RC/GIS/1388748 | RC | 2021-08-23 | On Going | 154967 | 2198 | 171423 | 328588 | 123408 | 0 | 0 | 123408
354 | Earthwork for road with Jhama Bats from the Shop of Haralal Sarkar to the L/O Priyolal Sarkar at Be | 3201009009/RC/GIS/1405980 | RC | 2021-11-21 | On Going | 158571 | 2249 | 175084 | 335904 | 107196 | 0 | 0 | 107196
355 | Excavation of farm pond at the land of Subhash Mondal Beraberia | 3201009009/WC/321002040926957 | WC | 2021-07-01 | On Going | 186520 | 0 | 3000 | 189520 | 183753 | 5751 | 0 | 189504
356 | Farm pond of Priyalal Sarkar at Beraberia VIII | 3201009009/WC/PP/1022115 | WC | 2020-05-19 | Completed | 427798 | 0 | 3000 | 430798 | 0 | 0 | 2678.57 | 2678.57

## Sector_Wise
Sector | Wage Amount | SSK Amount | Material Amount | Total
DP | 10224 | 0 | 2678.57 | 12902.57
FP | 407740 | 17262 | 10678.57 | 435680.57
IF | 4330038 | 13464 | 11357.14 | 4354859.14
RC | 1098265 | 119571 | 3712760 | 4930596
WC | 183753 | 5751 | 2678.57 | 192182.57

## Abstract
Tax Paid During 2021-22 |  |  |  |  | 172645.14
Amount Disbursed through E-FMS in FY : 2021-2022(In Lakh) |  |  |  |  | Wage | Material(SSK, SK, Material & Tax) | Admin
[5 empty] | 60.3 | 40.69 | 1.04
Employment Provided | Households | Persons | Persondays
| 527 | 610 | 31397
Average PD |  |  | 59.58
Average Wage Per PD |  |  | 190.48
Financial Year |  | Wage | SSK | Material
21-22 |  | 5980386 | 16614 | 0
20-21 |  | 49634 | 139434 | 3740152.85